## Schedule
| CMER Master Project Schedule | [45 empty] | All critical projects are to be completed by 2031 by WAC | [14 empty] | HCP over so all projects to b e completed by 2046
| Recommended FP HCP Adaptive Management Program Priority Projects |  | Assumed Annual Cost
| 5/29/14 - Draft Suggestions for revision to discuss with CMER and Policy |  | 75000 | 150000 | 350000 | 150000 | 75000
| Project | Project Priority | Years by Study Phase | [6 empty] | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 |  |  | Completion |  |  | Settlement Agreement | Project Priority | Recommend Action
|  |  | St Design | Site Selection | Implementation | Anal & Rpt Writing | Review & Approval | Total years | Total Cost | STD1 | STD2 | SS1 | IMPL1 | IMPL2 | IMPL3 | IMPL4 | IMPL5 | IMPL6 | A&W1 | A&W2 | RA&1 | R&A2 | TOTAL |  | Date | 2013 | 2014 |  |  |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052
Administrative and Support Staff
| CMER Science Staff | [24 empty] | 560000 | 560000 |  |  |  | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000 | 601000
| Project Support (includes 100K contingency fund) | [24 empty] | 337000 | 437000 |  |  |  | 487000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000 | 387000
| Project Administration | [24 empty] | 312000 | 267000 |  |  |  | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000 | 267000
MS Prioritized Projects Completed
| Bull Trout Overlay Solar Radiation | [26 empty] | Yes | 1 | delete | 2015: 0
| Bull Trout Overlay Temperature/Shade | [26 empty] | Yes | 1 | delete | 2015: 0
| Mass Wasting Effectiveness Monitoring | [26 empty] | Yes | 1 | delete | 2015: 0
#REF! | Westside Type N BCIF | 5 | Take from current budget sheet | [5 empty] | 157000 | [14 empty] | 0 |  |  | 81000 | Yes | 5 | delete | 2015: 0
Projects almost finished
#REF! | Eastside Type F Riparian Effectiveness (BTO add-on) | 1 |  |  |  | 2 | 2 | 4 | 450000 | [14 empty] | 75001 |  | 45000 | 30000 | Yes | 1 | delete (essentially complete | 2015: 0
8 | Buffer Integrity - Shade effectiveness (amphibian response) | 1 | [21 empty] | 81001 | CWA 2012 | 25000 | 26000 | Yes | 1 | retain | 2015: 30000
#REF! | Forest Practices and Wetlands Systematic Literature Review | 1 | [6 empty] | 50000 | [14 empty] | 167001 | CWA 2012 | 50000 | 57000 | Yes | 1 | retain | 2015: 60000
#REF! | Wetlands Program Research Strategy | 2 | [22 empty] | CWA 2013 |  | 50000 | Yes | 2 | retain | 2015: 33000
#REF! | Type F and N Extensive Westside - Temperature (Baseline status) | 1 |  |  |  |  | 1 | 1 | 75000 | [12 empty] | 75000 |  | 32501 | CWA 2015 | 7500 | 15000 | Yes | 1 | retain | 2015: 10000
6 | Eastside Type N Forest Hydrology | 1 | [6 empty] | 450000 | [14 empty] | 965001 |  | 350000 | 190000 | Yes | 1 | retain | 2015: 425000
| RMZ birds | [26 empty] | No |  | retain | 2015: 2000
#REF! | Eastern Washington Riparian Assessment (EWRAP) | 1 | [21 empty] | 150001 |  | 50000 | 50000 | Yes | 1 | revisit | 2016: 50000
#REF! | Riparian Hardwood Conversion | 1 | [21 empty] | 95001 |  | 2000 | 10000 | Yes | 1 | revisit | 2015: 10000; 2016: 73000
Projects on the ground and far along
1 | Type N Experimental Buffer Treatment Project in Hard Rock Lithologies | 1 | [21 empty] | 1034001 | CWA 2014 | 237000 | 179000 | Yes | 1 | retain | 2015: 304000; 2016: 214000; 2017: 100000
2 | Type N Experimental Buffer Treatment Project - Hard Rock- Amphibian Genetics - Post sample | 1 | [25 empty] | Yes | 1 | retain | 2015: 0; 2016: 200000; 2017: 200000; 2018: 85000; 2019: 40000
3 | Type N Experimental Buffer Treatment Project - Hard Rock- Amphibian Demographics/Channel Metrics | [7 empty] | 940000 | [14 empty] | 802000 | CWA NA |  | 25000 | No |  | retain | 2015: 0; 2016: 165000; 2017: 231000; 2018: 153000; 2019: 153000; 2020: 75000
4 | Type N Experimental Buffer Treatment Project in Hard Rock Lithologies - Temp/Sediment/Vegetation/Litterfall | [25 empty] | 163000 | No |  | retain | 2015: 134000; 2016: 320000; 2017: 190000; 2018: 119000; 2019: 0
5 | Type N Experimental Buffer Treatment Project - Soft Rock Lithologies | 1 | [21 empty] | 2256001 | CWA 2018 | 360000 | 360000 | Yes | 1 | retain | 2015: 344000; 2016: 382000; 2017: 360000; 2018: 216000; 2019: 153000; 2020: 81000
Other Projects
7 | Eastside Type N Riparian Effectiveness - Perennial | 1 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2695001 | CWA 2019 | 75000 | 75000 | Yes | 1 | revisit | 2015: 5000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
| Eastside Type N Riparian Effectiveness - Dry | [26 empty] | Yes | ? | revisit | 2015: 80000; 2016: 75000; 2017: 150000; 2018: 330000; 2019: 330000; 2020: 330000; 2021: 330000; 2022: 330000; 2023: 200000; 2024: 100000; 2025: 40000
#REF! | Unstable Slopes Criteria Evaluation and Development | 1 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 |  | 875001 | CWA Scope 2013 | 50000 | 50000 | Yes | 1 | retain | 2015: 150000; 2016: 150000; 2017: 150000; 2018: 150000; 2019: 100000; 2020: 75000
| Glacial Deep Seated - Develop Strategy (New as of 4/3/14- Policy) ($s are committed, but may need to revisit the description in the left-hand column) | [26 empty] | No |  | retain/expand | 2015: 50000
| Mass Wasting Landscape-Scale Effectiveness Monitoring | 2 | 2 | 1 | 4 | 2 | 2 | 11 | 2150000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 |  |  | 150000 | 150000 | 75000 | 75000 | 2150000 | 865002 | CWA Scope 2010 |  |  | Yes | 2 | revisit | 2016: 80000; 2022: 10000; 2023: 150000; 2024: 150000; 2025: 150000; 2026: 150000; 2027: 100000; 2028: 75000
#REF! | Forested Wetlands Effectiveness Study | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2565000 | CWA Scope 2013 | 75000 | 75000 | Yes | 2 | retain | 2015: 25000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
#REF! | Wetland/Stream Water Temp Interactions (Subquestion) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
#REF! | Wetland Hydrologic Connectivity (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
#REF! | Wetlands Management Zone Effectiveness Monitoring | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2565002 |  |  |  | Yes | 2 | retain | 2023: 25000; 2024: 100000; 2025: 250000; 2026: 360000; 2027: 360000; 2028: 360000; 2029: 360000; 2030: 360000; 2031: 250000; 2032: 100000; 2033: 40000
#REF! | Wetland/Stream Water Temp Interactions (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
#REF! | Wetland Hydrologic Connectivity (Add On) | 2 | 2 | 1 | 2 | 2 | 2 | 9 | 1450000 | 75000 | 75000 | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1450000 | 475002 |  |  |  | Yes | 2 | retain | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
#REF! | Westside Type F Riparian Prescription Monitoring | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2625002 | CWA Scope 2014 |  | 75000 | Yes | 2 | retain | 2015: 10000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
#REF! | Road Prescription-Scale Effectiveness Monitoring | 2 | 1 | 1 | 6 | 2 | 2 | 12 | 2775000 | 75000 |  | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2775000 | 40000 | CWA Scope 2013 |  | 75000 | Yes | 2 | retain | 2015: 25000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
#REF! | Road Sub-Basin-Scale Effectiveness Monitoring - Resample | 1 | 1 | 1 | 1 | 1 | 2 | 6 | 900000 |  |  | 150000 | 350000 | 350000 |  |  |  |  | 150000 |  | 75000 | 75000 |  | 1000001 | CWA 2018 |  |  | Yes | 1 | revisit | 2023: 75000; 2024: 350000; 2025: 350000; 2026: 150000; 2027: 75000
#REF! | Watershed Scale Assessment of Cumulative Effects (sed and temp) (roads and riparian) | 2 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2580002 | CWA Scope 2016 |  |  | Yes | 2 | retain | 2026: 40000; 2027: 100000; 2028: 250000; 2029: 360000; 2030: 360000; 2031: 360000; 2032: 360000; 2033: 360000; 2034: 250000; 2035: 100000; 2036: 40000
#REF! | Amphibians in Intermittent Streams | 2 | 1 | 1 | 3 | 1 | 2 | 8 | 1575000 | [14 empty] | 2630002 | CWA Scope 2016 |  |  | Yes | 2 | retain (d) | 2019: 40000; 2020: 150000; 2021: 250000; 2022: 360000; 2023: 360000; 2024: 360000; 2025: 360000; 2026: 360000; 2027: 250000; 2028: 100000; 2029: 40000
3 | Wetlands Intensive Monitoring | 6 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 | 1800000 | 1830000 |  |  |  | Yes | 6 | retain (c) | 2031: 40000; 2032: 100000; 2033: 250000; 2034: 360000; 2035: 360000; 2036: 360000; 2037: 360000; 2038: 360000; 2039: 250000; 2040: 100000; 2041: 40000
#REF! | Type F Experimental Buffer Treatment (maybe use to address gaps any unaswered F questions) | 3 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 2580000 |  |  |  | Yes | Unspecified | revisit | 2025: 40000; 2026: 100000; 2027: 250000; 2028: 360000; 2029: 360000; 2030: 360000; 2031: 360000; 2032: 360000; 2033: 250000; 2034: 100000; 2035: 40000
#REF! | Pathways of Riparian Stand Development to Maturity (Westside) | 4 | 1 | 1 | 2 | 1 | 2 | 7 | 1225000 | 75000 |  | 150000 | 150000 | 150000 |  |  |  |  | 150000 |  | 75000 | 75000 | 825000 | 785000 |  |  |  | Yes | 4 | revisit | 2025: 10000; 2026: 150000; 2027: 150000; 2028: 150000; 2029: 150000; 2030: 100000; 2031: 75000
#REF! | Type F Performance Target Validation (Westside) | 6 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 | 1800000 | 785000 |  |  |  | Yes | 6 | revisit | 2027: 10000; 2028: 150000; 2029: 150000; 2030: 150000; 2031: 150000; 2032: 100000; 2033: 75000
[24 empty] | TOTAL |  | 2535500 | 2875000 |  |  |  | 3052000 | 3464000 | 3736000 | 3848000 | 3611000 | 3506000 | 3375000 | 3495000 | 3165000 | 2915000 | 2765000 | 2665000 | 2650000 | 2800000 | 2775000 | 2685000 | 2590000 | 2375000 | 2280000 | 1965000 | 1755000 | 1655000 | 1615000 | 1615000 | 1505000 | 1355000 | 1295000 | 1255000 | 1255000 | 1255000 | 1255000 | 1255000 | [5 empty] | 0
| MP listed projects with greater questions on need (difference from $4 million) | [29 empty] | 948000 | 536000 | 264000 | 152000 | 389000 | 494000 | 625000 | 505000 | 835000 | 1085000 | 1235000 | 1335000 | 1350000 | 1200000 | 1225000 | 1315000 | 1410000 | 1625000 | 1720000 | 2035000 | 2245000 | 2345000 | 2385000 | 2385000 | 2495000 | 2645000 | 2705000 | 2745000 | 2745000 | 2745000 | 2745000 | 2745000
#REF! | Van Dykes Salamander Project | [26 empty] | Yes | Unspecified | Revisit | 2015: 56000; 2016: 284000; 2017: 103000; 2018: 266000; 2019: 103000
#REF! | Type N Extensive Eastside - Temperature (Baseline status) | 2 | 1 | 1 | 2 | 2 | 2 | 8 | 1375000 | 75000 |  | 150000 | 350000 | 350000 |  |  |  |  | 150000 | 150000 | 75000 | 75000 | 1375000 | 475002 | CWA 2015 |  | 25000 | Yes | 2 | Discuss | 2016: 150000; 2017: 150000; 2018: 150000; 2019: 0
| Type F Extensive East & Westside - Vegetation (Baseline status) | [26 empty] | Yes | 3 | Discuss | 2015: 0; 2016: 100000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000; 2021: 100000
| Type F Extensive East & Westside - Temperature (Resample) | [26 empty] | Yes | 3 | Discuss | 2015: 0; 2019: 150000; 2020: 350000; 2021: 350000; 2022: 150000; 2023: 75000; 2024: 75000; 2025: 350000; 2026: 350000; 2027: 150000; 2028: 75000; 2029: 75000
| Type F Extensive East & Westside - Vegetation (Resample) | [26 empty] | Yes | 3 | Discuss | 2015: 0; 2031: 150000; 2032: 150000; 2033: 150000; 2034: 150000; 2035: 75000; 2036: 75000
| Type N Extensive East & Westside - Vegetation (Baseline status) | [26 empty] | Yes | 4 | Discuss | 2015: 0; 2016: 150000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 100000
| Type N Extensive East & Westside - Temperature (Resample) | [26 empty] | Yes | 4 | Discuss | 2015: 0; 2023: 150000; 2024: 350000; 2025: 350000; 2026: 150000; 2027: 75000; 2028: 75000; 2029: 150000; 2030: 350000; 2031: 350000; 2032: 150000; 2033: 75000; 2034: 75000
| Type N Extensive East & Westside - Vegetation (Resample) | [26 empty] | Yes | 4 | Discuss | 2015: 0; 2030: 150000; 2031: 150000; 2032: 150000; 2033: 150000; 2034: 75000; 2035: 75000
#REF! | Effectiveness of RMAP Fixes | 4 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 625004 |  |  |  | Yes | 4 | Remove or demote to alternates list | 2015: 0; 2030: 150000; 2031: 150000; 2032: 150000; 2033: 100000; 2034: 75000
| Road Surface Erosion Model Validation/ Refinement | [26 empty] | Yes | 6 | Remove or demote to alternates list | 2015: 0; 2028: 10000; 2029: 150000; 2030: 150000; 2031: 150000; 2032: 150000; 2033: 100000; 2034: 75000; 2035: 350000; 2036: 150000; 2037: 100000
1 | Wetlands Overlay Project | 6 | 1 |  | 1 | 2 | 2 | 6 | 875000 | 75000 |  |  | 350000 | [5 empty] | 150000 | 150000 | 75000 | 75000 | 875000 | 0 |  |  |  | Yes | 6 | Remove or demote to alternates list | 2015: 0; 2019: 10000; 2020: 150000; 2021: 150000; 2022: 150000; 2023: 150000; 2024: 100000; 2025: 75000
2 | Wetlands Mitigation Effectiveness (deprioitized by CMER/ Policy) | 6 | 2 | 1 | 6 | 2 | 2 | 13 | 2850000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 350000 | 150000 | 150000 | 75000 | 75000 | 2850000 | 0 |  |  |  | Yes | 6 | Remove or demote to alternates list | 2015: 0; 2019: 10000; 2020: 150000; 2021: 150000; 2022: 150000; 2023: 150000; 2024: 100000; 2025: 75000
#REF! | Mass Wasting Buffer Integrity - Windthrow | 6 | [5 empty] | 0 | 0 | [14 empty] | 0 |  |  |  | Yes | 6 | Replace with strategy | 2015: 0; 2019: 10000; 2020: 150000; 2021: 150000; 2022: 150000; 2023: 150000; 2024: 100000; 2025: 75000
#REF! | Windthrow Frequency, Distribution and Effects | 3 | 2 | 1 | 3 | 2 | 2 | 10 | 1800000 | 75000 | 75000 | 150000 | 350000 | 350000 | 350000 |  |  |  | 150000 | 150000 | 75000 | 75000 | 1800000 | 2580003 |  |  |  | Yes | 3 | Replace with strategy | 2023: 40000; 2024: 100000; 2025: 250000; 2026: 360000; 2027: 360000; 2028: 360000; 2029: 360000; 2030: 360000; 2031: 250000; 2032: 100000; 2033: 40000
#REF! | Eastside Type N BCIF | 3 | 1 | 1 | 9 | 2 | 2 | 15 | 3825000 | 75000 |  | 150000 | 350000 | 350000 | 350000 | 350000 | 350000 | 1400000 | 150000 | 150000 | 75000 | 75000 | 3825000 | 3 |  |  |  | Yes | 3 | Discuss combinin with other eastside studies | 2015: 0
| Type N Experimental Buffer Treatment in Hard Rock | [26 empty] | Yes | 6 | Remove
Projects on MS "Other Projects" list
| Landslide Classification (deep seated landslides) | [26 empty] | Alternate List |  | Revisit after subgroup | 2016: 100000
| Groundwater Recharge Modeling and Model Refinement | [26 empty] | Alternate List |  | Revisit after subgroup | 2016: 60000
| Evapo-Transpiration Model Refinement | [26 empty] | Alternate List |  | Revisit after subgroup | 2017: 60000; 2021: 40000; 2022: 100000; 2023: 250000; 2024: 360000; 2025: 360000; 2026: 360000; 2027: 360000; 2028: 360000; 2029: 250000; 2030: 100000; 2031: 40000
| Shallow Rapid Landslide Screen (Eastside) | [26 empty] | Alternate List |  | Move to DNR | 2018: 10000; 2019: 150000; 2020: 150000; 2021: 150000; 2022: 150000; 2023: 100000; 2024: 75000
| Intensive Watershed-Scale Monitoring to Assess Cumulative Effects (Roads Program) | [26 empty] | Alternate List |  | Remove
| Eastside Type F Channel Wood Characterization | [26 empty] | Alternate List |  | Retain on alternate list | 2026: 10000; 2027: 150000; 2028: 150000; 2029: 150000; 2030: 150000; 2031: 100000; 2032: 75000
| DFC Aquatic Habitat | [26 empty] | Alternate List |  | Discuss | 2028: 10000; 2029: 150000; 2030: 150000; 2031: 150000; 2032: 150000; 2033: 100000; 2034: 75000
| Eastside Tailed Frog Distribution Study | [26 empty] | Alternate List |  | Retain on alternate list | 2029: 10000; 2030: 150000; 2031: 150000; 2032: 150000; 2033: 150000; 2034: 100000; 2035: 75000
| DFC Site Class Map Validation | [26 empty] | Alternate List |  | Remove | 2031: 10000; 2032: 150000; 2033: 150000; 2034: 150000; 2035: 150000; 2036: 100000; 2037: 75000
| Tailed Frog meta-Analysis | [26 empty] | Alternate List |  | Discuss | 2020: 100000; 2021: 40000
| Tailed Frogs and Parent Geology | [26 empty] | Alternate List |  | Retain on alternate list until hard rock is done | 2021: 10000; 2022: 150000; 2023: 150000; 2024: 150000; 2025: 150000; 2026: 100000; 2027: 75000
| DFC Trajectory Model Validation | [26 empty] | Alternate List |  | Remove | 2032: 10000; 2033: 150000; 2034: 150000; 2035: 150000; 2036: 150000; 2037: 100000; 2038: 75000
| Eastside Temperature Nomograph | [26 empty] | Alternate List |  | Discussion | 2032: 10000; 2033: 150000; 2034: 150000; 2035: 150000; 2036: 150000; 2037: 100000; 2038: 75000
| Hydrogeomorphic Wetland Classification System | [26 empty] | Alternate List |  | Remove | 2032: 10000; 2033: 150000; 2034: 150000; 2035: 150000; 2036: 150000; 2037: 100000; 2038: 75000
| Annotated Bibliography Riparian Hardwood Conversion | [26 empty] | Alternate List |  | Remove | 2032: 10000; 2033: 150000; 2034: 150000; 2035: 150000; 2036: 150000; 2037: 100000; 2038: 75000
Appear done or not to be CMER Research
| Red Alder Growth and Yield Model | [26 empty] | Alternate List | Completed | Remove | 2015: 0
| Tailed Frog Literature Review | [26 empty] | Alternate List | Near Complete | Remove | 2015: 0
| Groundwater Conceptual Model | [26 empty] | Alternate List | Completed | Remove | 2015: 0
| Overlay Project (Wetlands Mapping) | [26 empty] | Alternate List | Too Late? | Remove | 2016: 10000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000
| DFC Plot Width Standardization | [26 empty] | Alternate List | Too Late? | Remove | 2015: 0
| Landslide Hazard Zonation (priority 3 watersheds) | [26 empty] | Alternate List | DNR task? | DNR | 2016: 10000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000
| Board Manual Revision | [26 empty] | Alternate List | DNR task? | DNR | 2015: 0
| DNR GIS Wetlands Data Layer | [26 empty] | Alternate List | DNR task? | DNR | 2015: 0
| Extensive Fish Passage Trend Monitoring | [26 empty] | Alternate List | DNR task? | DNR | 2015: 0
| Consistency and Accuracy of CMZ Boundary Delineations | [26 empty] | Alternate List | DNR task? | DNR | 2016: 10000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000
| Yakima River Radiotelemetry | [26 empty] | Alternate List | WDFW task? | Remove but get copy from WDFW if done | 2015: 0
| CMZ Screen and Aerial Photo Catalog and CMZ Boundary Identification Criteria | [26 empty] | Alternate List | BM Criteria established | Remove and DNR | 2015: 0
Program listed without any projects in Master Schedule
| Forest Chemicals Program (Effectiveness) | [26 empty] | Alternate List |  | See specific study recommendations for wetlands
| Fish Passage Effectiveness/Validation Monitoring Program | [26 empty] | Alternate List | DNR task? | WDFW? | 2032: 40000; 2033: 100000; 2034: 250000; 2035: 360000; 2036: 360000; 2037: 360000; 2038: 360000; 2039: 360000; 2040: 250000; 2041: 100000; 2042: 40000
| Mass Wasting Validation Program (Intensive) | [26 empty] | Alternate List |  | Retain on Alt. until MW strategy | 2032: 40000; 2033: 100000; 2034: 250000; 2035: 360000; 2036: 360000; 2037: 360000; 2038: 360000; 2039: 360000; 2040: 250000; 2041: 100000; 2042: 40000
| CMZ valadation Program (no specific projects suggested) | [26 empty] | Alternate List |  | Remove | 2016: 10000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000
"New" Projects that would appear needed eventually but that are not in workplan:
| Chemical Effects to Forested Wetlands (New study in Wetlands Strategy) | [26 empty] | No |  | Retain on alt list until strategy | 2032: 40000; 2033: 100000; 2034: 250000; 2035: 360000; 2036: 360000; 2037: 360000; 2038: 360000; 2039: 360000; 2040: 250000; 2041: 100000; 2042: 40000
| Eastside Type F Effectiveness (New study for remaining strata) | [26 empty] | No |  | Retain until BTO discussion | 2018: 40000; 2019: 100000; 2020: 250000; 2021: 360000; 2022: 360000; 2023: 360000; 2024: 360000; 2025: 360000; 2026: 250000; 2027: 100000; 2028: 40000
| Revise Shallow Rapid Lanslide Screen (westside) using LiDAR | [26 empty] | No |  | DNR and MW Strategy discussion | 2016: 10000; 2017: 150000; 2018: 150000; 2019: 150000; 2020: 150000; 2021: 100000; 2022: 75000
| Wetlands/Roads Interaction study (possible replacement for Wetland Mitigation Effect. study) | [26 empty] | No |  | Retain until Wet Strategy | 2032: 40000; 2033: 100000; 2034: 250000; 2035: 360000; 2036: 360000; 2037: 360000; 2038: 360000; 2039: 360000; 2040: 250000; 2041: 100000; 2042: 40000
[24 empty] | TOTAL |  | 1281500 | 1500000 |  |  |  | 3052000 | 4074000 | 4996000 | 5098000 | 5091000 | 5806000 | 4975000 | 4930000 | 4740000 | 4685000 | 4810000 | 4245000 | 3920000 | 3880000 | 4070000 | 4245000 | 4240000 | 3950000 | 4295000 | 4340000 | 4520000 | 4020000 | 3630000 | 3355000 | 2945000 | 2355000 | 1695000 | 1415000 | 1255000 | 1255000 | 1255000 | 1255000
Should every Rule Group have a final Placeholder Study to address any final issues/questions?
| Stream Typing (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Type N Riparian Prescriptions (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Type F Riparian Prescriptions (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Unstable Slopes (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Roads (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Fish Passage (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Pesticides (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Wetlands Protection (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
| Wildlife (to address remaining outstanding questions) | [26 empty] | No |  | Discuss
Note on AA54: Hicks, Mark (ECY): Ecology supports 2021 date and may drop this milestone if RMAP program improvements prove sufficient.
Note on AG8: ceh: FY15: includes $100,000 for LiDAR water typing model pilots
Note on AJ32: Mark Hicks: Based on consultation with Bill E I dropped FY18 and 19 by 40% assuming harvets occur as per agreement with landowners. This was a change from 360K 2018 and 255K in 2019.
Note on AH24: Mark Hicks: This may end up not being requested and can be done anytime using the final data.
Note on AH25: Mark Hicks: Policy needs to determine if this 10-year free to grow data is desirable.
Note on AG36: Mark Hicks: For TWIG to have outside entity as coordinator on field data collection with the other consultants, and to keep on retainer to begin help TWIG as a lead writer developing study desgin once data is collected.
Note on AH28: Mark Hicks: Final cost heavily depends on the nature of the review comments received, but will probably be less than budgeted if reanalysis and major re-write is not needed.
Note on AK57: Mark Hicks: Project moved out two years since need for study will not be determined until hard rock amphibian analyses are complete. Is there reason to assume it will be 100K to develop a study design?
Note on AR56: Moved out to after W. F Effectiveness study is complete so that knowledge plus what is learned from the Type N studies can go into developing a study design
Note on B80: Mark Hicks: Should we assume effectiveness studies will be used to cover this informaiton need or keep this stand alone project?
Note on B78: Mark Hicks: CMER suggests that we just turn this into a requirement to develop a strategy for incorporating windthrow into other planned studies, rather than having a stand alone windthrow study. Probably need to revisit what policy agreed to.
Note on B77: Mark Hicks: Recommend changing this to a more generic "Road/wetlands interactions" study. Roads will remain a topic of interest in the Wetlands research strategy.
Note on AG66: mhic461: Phase I start of three phase project. Can break up timing of different phases. Originally this was 56K, 237K, 103K, 266K, and 103K. Currently the second year of phase one includes costs for first year of phase 2.
Note on B61: mhic461: Is this a priority? The purpose of this project is to determine the development sequence of younger stands of various species compositions and densities to mature stands. The study is intended to inform management of uneven-aged stands and those of low density or mixed composition.
Note on AO54: mhic461: Moved from 2021 to manage budget bump.
Note on AP54: mhic461: I broke a 700K field season into two years of 350K each.
Note on B62: mhic461: This project will evaluate the validity of the Type F performance targets and the measures of success in meeting resource objectives. Will this really be a stand alone project or will we use the efectiveness study results to make recommendations?
Note on B100: mhic461: No longer stand alone project. RSAG has made the literature review a component of HWC study report rather than a stand alone annotated bibliograpy. Suggest deletion.
Note on B96: mhic461: First CMER needs to know if there is a need to set different prescriptions based on occupation by tailed frog, then we will know if this project is needed.
Note on B97: mhic461: This project would assess the accuracy of the DFC model in predicting riparian stand growth and trajectory from harvest age to the DFC target (age 140). This project will be designed to validate the DFC model as a tool to predict trajectory to the DFC target for both conifer-dominated and mixed stands. CMER believes this is a DNR Operational project since mixed stands at the present and CMER has no control over the model. Not clear how CMER would validate the model.
Note on B103: mhic461: Completed.
Note on B114: mhic461: CMER does not have role in this incompleted old project. Suggest deletion.
Note on B115: mhic461: CMER believes a Board Manual was subsequently developed that supercedes need for this project. Suggest deletion.
Note on B113: mhic461: This seems like compliance monitoring. Is it still a project for CMER?
Note on B112: mhic461: Will operational checks on fish passage as part of RMAP program suffice to provide status of fish passage on regional scale and how conditions are changing over time?
Note on B107: mhic461: This is really a strategy for combining research efforts - collecting informaiton on wetlands while doing other CMER topical research. Not a study, and pretty late to do this now in a formal way.
Note on B99: mhic461: Should be determined necessary and viable based on other planned wetland effectiveness studies. May be accomplished by these other projects. Outcome if needed would be more wetland types in the rules having different prescriptions. Should this be on list until we determine it is appropriate to regulated based on different HGM types?
Note on B98: mhic461: Attempt failed. Not viewed as a sound scientific concept. Is the nomograph even needed given East F BTO study findings.
Note on AG17: mhic461: Internal so no cost but what about staff resources.?
Note on AG35: mhic461: Greg suggests allocating money to begin finding sites in 2015. But this part of budget was approved and going to Boartd.
Note on B68: Mark Hicks: Suggest deleting all of the extensive vegetation and temperature resample projects from main list given questional benefits and unclear methods and targets for monitoring. Alternatively just conduct a single baseline for vegetation out in the future if it can be done in a manner that assessess applicability of the results from the effectiveness monitoring studies. Probably no sooner than 2018 after completion of Type N soft rock study and after Westside F prescription monitoring study design has been established.
Note on B45: mhic461: Anticipated to major experimental studies with temp and connectivity as add-on costs.
Note on AG15: mhic461: Internal so no cost but what about staff resources.?
Note on AL32: mhic461: This represents a 5th year post resample of vegetation to sync up with West BCIF data.
Note on B105: mhic461: Project almost complete, and no budget needed.
Note on B95: mhic461: Not high priority and best scheduled after 2019, or deleted for now. Requires adjusting literature findings based on our new kinowledge of how temperture may have biased detection.
Note on B108: mhic461: CMER believes the timeframe for doing this study has passed. This should be deleted.
Note on B111: mhic461: CMER believes this is a DNR Operational task, and not a science task and should be deleted.
Note on B75: mhic461: Is this still a priority project. Perhaps it should be on the back up list.
Note on B121: mhic461: No project established but intended to address question: Will the physical processes that drive channel migration change appreciably due to the application of forest practices rules?
Note on B106: mhic461: If complete, why not delete from list?
Note on B109: mhic461: Nine of original 22 priority watersheds were completed before ending phase 3. This is probably a DNR operational task, so perhaps should remove from CMER list.
Note on B110: mhic461: FPB mandated this to Board Staff/DNR to accomplish. Remove from CMER project list.
Note on AJ36: mhic461: Field monitoring cost estimates dropped from 360K/yr to 330K/yr anticipating some savings if done concurrently with perennial flow study.
Note on AO36: mhic461: Analysis costs lowered from 250K to 200K expecting some savings due to staff efficiency if done concurrent with perennial flow study.
Note on AL57: mhic461: Default costs raised from 100K for first year of site acquisition to 150k in recognition of greater logistical challenges in finding amphibian study sites.
Note on B74: mhic461: Not clear what this does that would be distinct from the Road Prescription Scale study and DNR Operations.
Note on AK31: mhic461: Dropped the 75K that was in 2019 given policy has provided the ability for this extended montioring to be completed without going through ISPR.
Note on B42: mhic461: UPSAG does not recommend this study - comments include "it can't be done" and "the answer is obvious and it is a waste of resources". It is a key FFR question however so perhaps include seed money for Pilot or RFP to see if method may exist to get done with Lidar etc. It could also be moved out in time and serve as a validation study to be done after any further rule improvements are in place.
Note on AH42: mhic461: Money to solicit ideas for how to conduct this study via an RFP.
Note on B76: mhic461: This is really a strategy for combining research efforts - collecting informaiton on wetlands while doing other CMER topical research. Not a study, and pretty late to do this now in a formal way.
Note on AM85: mhic461: Could replace in time with the amph in intermittent stream study - if this additional field study is determined necessary. Costs may not adequately fit this project.
Note on AK30: mhic461: Aimee says these last out-year costs assume it will need to go through the ISPR process.
Note on AK67: mhic461: Dropped 50K for last year given policy has provided the ability for this extended montioring to be completed without going through ISPR.
Note on B84: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. Uses modeling to try and determine what part of recharge areas are most influential on landslide movement.
Note on B83: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. UPSAG does not recommend this in current form. UPSAG would prefer to empirically monitor movement of active landslides where harvest occurred in groundwater recharge area.
Note on B85: mhic461: Moved to main MS worksheet to support Board prioritzation of GDSL program. UPSAG does not recommend pursuing this project. Expects basic science questions would not be resolved.
Note on AJ86: mhic461: No sound basis for this estimate. Assumes only review by two qualified FTE and not data acquisition costs.
Note on B126: mhic461: Costs estimate would not include acquisition of LiDAR. Project a recommendation of UPSAG.
Note on B90: mhic461: Project needs to be rescoped to proceed as it was to use the EWRAP data set. Too much time has now passed. May be needed if want to establish LWD performance targets on Eastside.
Note on B91: mhic461: Potentially viable and relevant: determine the range of aquatic habitat associated with mature (DFC) riparian forest conditions. Perhaps tied in with Performance Target Validation research. Do we, however, need a separate project for DFC age stands, or clarify this is a subpart to F-stream validation monitoring?
Note on B92: mhic461: Should be tied to the results of the Eastside N effect study. If no effect on temperature than perhaps no reason to do the study.
Note on B94: mhic461: Purpose would be to develop method to correct site class map designations for RMZs. Scoping document was prepared and presented to policy.
Note on B79: mhic461: CMER would like to replace this with a strategy on incorporation within other projects.
Note on AH36: mhic461: Site acquisition costs reduced if dry and perennial done at same time.
Note on B54: mhic461: What did the first sample actually cost?
Note on B86: mhic461: Is this really a DNR project?
Note on AG40: mhic461: Uses default costs and assumes analysis follwed by potential case study.
Note on AH31: mhic461: This year includes export monitoring for nutrients - which were initially elevated post harvest.
Note on B31: mhic461: Extended monitoring to look at recovery of variables increased post harvest - temperature and nutrients. Also, temperature in years 2016 and 2017 are in support of the analysis work for amphibian demographics.
Note on AG31: mhic461: Optional year for study, but it would cost to maintain monitoring network almost the same if we do not collect the data.
Note on AH67: mhic461: PI suggests this is probably too soon to initiated and suggested 2017.
Note on B35: mhic461: The perennial and dry studies are matched in time to gain economies of scale and allow consideration of project integration.
Note on B81: mhic461: There was money placed in out year that no one in CMER understands the purpose of.
Note on B14: mhic461: Complete
Note on B12: mhic461: Complete
Note on B13: mhic461: Complete
Note on B117: mhic461: Do we budget and plan anything for programs where the projects have not yet been established?
Note on AH68: mhic461:
Note on B60: mhic461: Can we formally ackowledge ability to use this to alternatively fill any "gaps" in knowledge? The purpose of this project is to test the effectiveness of alternative treatments which are not part of the current FFR/HCP prescription package.
Note on B88: mhic461: This is a program and is already listed in the prioritized list of MS projects.
Note on B56: mhic461: Not an actual project title. Currently represented in workplan at the program level by a general description that it integrates issues spanning the riparian and road rule groups.
Note on B119: mhic461: Appears to be an operational compliance/trends issue.
Note on B120: mhic461: The key objective of projects developed in this program will be to understand, at a watershed scale, the cumulative effects of different sediment loads in the context of rates of management-induced versus natural landslides.
Note on B124: mhic461: Study newly identified in the forthcoming Wetlands Research Strategy.
Note on B125: mhic461: Gap in knowledge on prescription effectiveness noted after completion of eastside BTO temp/shade study.
Note on B127: mhic461: New project identified in forthcoming Wetlands Research Strategy.
Note on B130: mhic461: Alternative would be to rely on the intensive and cumulative effects studies in the workplan to address any final informaitonal needs on rule effectiveness.

## OtherProjects
CMER Work Plan Projects Listed Below will be Prioritized and Budgeted at a Later Date by CMER/Policy.
Note: Order is not representative of review prioity. Some project may be dropped pending review of recent literature and some
projects may be added pending final results of CMER projects, further review and evaluation of "critical questions"
in CMER's Work Plan, and unforeseen needs of Policy and the Board. Projects already on Policy's "Task List" do not apply.
Type N Amphibian Response Program (Effectiveness)
Tailed Frog Literature Review
Tailed Frog meta-Analysis
Tailed Frogs and Parent Geology
DFC Validation Program (Rule Tool)
DFC Plot Width Standardization
DFC Site Class Map Validation
DFC Trajectory Model Validation
DFC Aquatic Habitat
Red Alder Growth and Yield Model
Eastside Type F Riparian Rule Tool Program
Eastside Temperature Nomograph
Eastside Type F Channel Wood Characterization
Yakima River Radiotelemetry
Westside Type F Riparian Effectiveness Program
Type F Performance Target Validation
Eastside Type F Riparian Effectiveness Program
Groundwater Conceptual Model
Hardwood Conversion Program
Annotated Bibliography Riparian Hardwood Conversion
CMZ Delineation Program
CMZ Screen and Aerial Photo Catalog and CMZ Boundary Identification Criteria
Consistency and Accuracy of CMZ Boundary Delineations
CMZ Validation Program
Projects yet to be Identified
Unstable Landform Identification Program (Rule Tool)
Shallow Rapid Landslide Screen for GIS (Eastside)
Landslide Hazard Zonation (priority 3 watersheds)
Glacial Deep-Seated Landslides Program (Rule Tool)
Evapo-Transpiration Model Refinement
Landslide Classification
Groundwater Recharge Modeling and Model Refinement
Board Manual Revision
Mass Wasting Validation Program (Intensive)
Projects yet to be identified
Roads Validation Program and Cumulative Sediment Effects
Intensive Watershed-Scale Monitoring to Assess Cumulative Effects
Fish Passage Effectiveness/Validation Monitoring Program
Projects yet to be Identified
Extensive Fish Passage Monitoring Program
Extensive Fish Passage Trend Monitoring
Forest Chemicals Program (Effectiveness)
Projects yet to be Identified
Wetlands Mapping Tools Program (Rule Tool)
DNR GIS Wetlands Data Layer
Hydrogeomorphic Wetland Classification System
Overlay Project (Wetlands Mapping)

## Sheet1
Projects almost finished |  | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047 | 2048 | 2049 | 2050 | 2051 | 2052
Forest Practices and Wetlands Systematic Literature Review | X
Wetlands Program Research Strategy | X
Planned priority projects |  | 2015: Design; 2016: Sites; 2017: Sites&Install; 2018: Pre 1; 2019: Pre 2; 2020: Harvest; 2021: Post 1; 2022: Post 2; 2023: Analysis; 2024: CMER; 2025: ISPR
Forested Wetlands Effectiveness Study |  | 2015: 25000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
Wetland/Stream Water Temp Interactions (Add On) |  | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
Wetland Hydrologic Connectivity (Add On) |  | 2016: 50000; 2017: 50000; 2018: 50000; 2019: 50000; 2020: 50000; 2021: 50000; 2022: 50000; 2023: 50000; 2024: 50000; 2025: 25000
Pesticides?
Wetlands Management Zone Effectiveness Monitoring |  | 2023: 25000; 2024: 100000; 2025: 250000; 2026: 360000; 2027: 360000; 2028: 360000; 2029: 360000; 2030: 360000; 2031: 250000; 2032: 100000; 2033: 40000
Wetland/Stream Water Temp Interactions (Add On) |  | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
Wetland Hydrologic Connectivity (Add On) |  | 2024: 50000; 2025: 50000; 2026: 50000; 2027: 50000; 2028: 50000; 2029: 50000; 2030: 50000; 2031: 50000; 2032: 50000; 2033: 25000
|  | Pesticides? | [19 empty] | 40000 | 100000 | 250000 | 360000 | 360000 | 360000 | 360000 | 360000 | 250000 | 100000 | 40000
Wetlands Intensive Monitoring |  | 2015: Cumulative Effects/Gap fullfillment?
MP listed projects requiring more discussion with Policy
Wetlands Overlay Project | $?
Wetlands Mitigation Effectiveness (deprioitized by CMER/ Policy) | $? | 2015: Roads Study?
DNR GIS Wetlands Data Layer | $?
Hydrogeomorphic Wetland Classification System | $?
Projects from Workplan that appear still to be missing
Forest Chemicals Program (no specific projects suggested) (WetSAG Strategy ) | $? | 2015: 40000; 2016: 100000; 2017: 250000; 2018: 360000; 2019: 360000; 2020: 360000; 2021: 360000; 2022: 360000; 2023: 250000; 2024: 100000; 2025: 40000
Note: If Pesticides is added on the forested wetlands study, seems more time will be needed for both site acquisition and harvest.
Note on A8: mhic461: Anticipate two major experimental studies with temp and connectivity as add-on costs.
Note on A18: Mark Hicks: Is this still a priority project. Perhaps it should be on the back up list. The purpose was to collect data on wetlands while doing other CMER research. With much of N work done, and no basis for integration established, this is a good idea that is too late and too undeveloped.
Note on A19: Mark Hicks: Is this still a priority project. Perhaps it should be on the back up list, or at least changed into a more generic "Road/wetlands interactions" study. It seems we determined we cannot really do an unbiased assessment of the use of the mitigation strategy. Should it be a part of the roads prescription scale study - would roads TWIG need WetSAG resources?
Note on A20: mhic461: CMER believes this is a DNR Operational task, and not a science task and should be deleted.
Note on A21: mhic461: Should be determined necessary and viable based on other planned wetland effectiveness studies. May be accomplished by these other projects. Outcome if needed would be more wetland types in the rules having different prescriptions. Should this be on list until we determine it is appropriate to regulated based on different HGM types?
Note on A25: mhic461: Addresses question of whether harvesting changes channel migration patterns.
Note on A24: mhic461: Would this likley be a stand alone study or an add on to the forested wetlands study?