## Flagging Milestone
CMER Project Flagging Process In October 2009, the Department of Ecology completed a 2009 Clean Water Act (CWA) review of the state's forest practices and adaptive management programs. A findings paper entitled "2009 Clean Water Act Assurances Review of Washington's Forest Practices Program, Examining the effectiveness of Washington's forest practices program in bringing waters into compliance with state water quality standards and the federal Clean Water Act " was completed in July of 2009. Based on their review, the Department of Ecology conditionally extended the CWA assurances. The extension was based on meeting a scheduled set of milestones for program improvements and research development. One of the CWA milestones included, "By December 2009, the AMP Manager with the assistance of the co-chairs of Policy and CMER will initiate a process for flagging projects for the attention of Policy that are having trouble with their design or implementation. This process should identify projects not proceeding on a schedule reflecting a realistic but expedient pace (i.e., a normal amount of time to complete scoping, study design, site selection, etc.)." The following sheets were used to develop a flagging process. The "Flagging Triggers" sheet contains the flagging process for formally meeting the CWA milestone.
Sheet "CMER Milestones and Tasks" contains the Major Milestones and associated tasks associated with most projects. The number of months for completing these are also included. The months in this and the "Flagging Triggers" sheet are consistent with each other. Sheet "CMER Tasks" also contains the major tasks associated with each of the major milestones, but presented in a different way. Again, the time periods are consistent with the other two sheets. A word of caution, the Major Milestone months should not generally be summed to calculate a total project time period (although it has been done in sheet "CMER Tasks". While the total project period will undoubtedly be long, many tasks can be worked on simultaneously. Further, this is a planning tool. Not all projects are the same. Some are more complex than others. Some have more stakeholders' interests. Timelines will vary. Nevertheless, this planning tool should help keep CMER focused and bring issues and disagreements to the forefront earlier than has been experienced in the past.
| 2010-10-01 | 2011-02-01 | 2011-07-01 | 2011-11-01 | 2012-02-01 | 2012-10-01 | 2012-12-01

## CMER Milestones and Tasks
CMER PROGRAM PROJECT STATUS SPREADSHEET
[6 empty] | Milestone | Task |  | Task |  | Task |  | Milestone | Task |  | Task |  | Task |  | Milestone | Task |  | Task |  | Task |  | Task |  | Milestone | Milestone |  | Milestone | Task |  | Task |  | Task |  | Task |  | Task |  | Milestone | Task |  | Task |  | Task |  | Task |  | Task |  | Task |  | Milestone
| Human Resources |  |  |  |  | CMER Project Planning Initiated | Project Charter Completed |  | Project Plan |  | CMER Supported Project Plan |  | CMER Approved Scoping Paper | Research Questions, Objectives, Data Needs, Options, and BAS Identified |  | Scoping Paper Approved for CMER Review |  | CMER Approved Scoping Paper |  | CMER Approved Final Study Design | Study Design Drafted and Approved |  | CMER Approved Study Design |  | ISPR Review of Study Design, Matrix, CMER Approval |  | CMER Approved Final Study Design |  | Final Study Plan to policy | Contract completed |  | Field Research Completed | Field Manual Completed |  | QA/QC methods & Plan Complete |  | Site selection Completed (As Applicable) |  | Data Collect Field Work Completed |  | Approval of Database |  | CMER Approved Final Project Rpt. Complete | Data Analysis, Including Statistical Analyses |  | SAG Approved Project Report (for CMER review) |  | CMER Approved Project Final Report (For ISPR Review) |  | ISPR Review of Project Report Complete w/ Completed Comment Matrix |  | CMER Approved Final Report |  | SAG/CMER Findings Report Completed |  | Final Report to policy
Estimated Timeframe (Months) | [5 empty] | 7 M | 2 M |  | 3 M |  | 2 M |  | 7 M | 4 M |  | 2 M |  | 1 M |  | 18 M | 6 M |  | 2 M |  | 8 M |  | 2 M |  | 1 M | 4 M |  | 15 + M | 3 M |  | 3 M |  | 5 M |  | PROJECT SPECIFIC |  | 4 M |  | 25 M | 5 M |  | 4 M |  | 3 M |  | 8 M |  | 2 M |  | 3 M |  | 1 M
|  | PM | PM | PI | NWIFC |  | START | FINISH | START | FINISH | START | FINISH |  | START | Finish | START | FINISH | START | FINISH |  | START | FINISH | START | FINISH | START | FINISH | START | FINISH |  | START | FINISH |  | START | FINISH | START | FINISH | START | FINISH | START | FINISH | START | FINISH | START | Start | Finish | START | FINISH | START | FINISH | START | FINISH | START | FINISH | START | FINISH | FINISH | General Status Comments
TYPE N RULE GROUP
WWA Type N Buffer Characteristics Integrity and Function (BCIF) - Re-sample | RSAG | Teresa | HH |  | DS |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Mar-15 | [11 empty] | Extended sampling field work completed September 2013. Data input and QA/QC done. Data and statistical analysis to occur early 2015.
Type N Experimental Buffer Treatment - Hard Rock (Report Writing) | RSAG LWAG |  | AK | AM | DS GS |  | N/A | N/A | N/A | N/A | N/A | N/A | [32 empty] | 2014-07-01 |  |  | 2013-05-01 | 2014-12-01 | [6 empty] | CWA 2014 | Coordinated review schedule set by chapter. Complete full draft of 17 chapters by Oct. 2014. Chapters will be forwarded onto ISPR Dec. 2014
Type N Experimental Buffer Treatment - Hard Rock - Amphibian Genetics Component | RSAG LWAG |  | AK | AM |  |  | N/A | N/A | N/A | N/A | N/A | N/A | [26 empty] | FY 2016 | [16 empty] | CWA 2014 | Part of original hard rock study design; need a second generation of the population for genetics component
Type N Experimental Buffer Treatment - Hard Rock - Amphibian Demographics & Channel Metrics | RSAG LWAG |  | AK | AM |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | [5 empty] | FY2013 | FY 2019 | [16 empty] | Extended field sampling proposed for Amphibian Demographics FY18, FY19. Extended Field sampling for Channel Metrics FY13, 14, 17, 18 and 19.
Type N Experimental Buffer Treatment - Hard Rock - Extended Sampling - Temp/ Sediment/ Veg./ Litter Fall | RSAG LWAG |  | AK | AM BE |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | 2013-04-01 | FY 2019 | [16 empty] | Extended field sampling: FY13, 14, 18 and 19.
Type N Experimental Buffer Treatment - Soft Rock | RSAG | Amy | HH | GS | GS |  | N/A | N/A | N/A | N/A | N/A | N/A | [7 empty] | CWA 2010 | [11 empty] | CWA 2011 | [7 empty] | FY 2017 | [15 empty] | CWA 2018 | Pre-harvest sampling FY 2013-2014, 2-year post-harvest sampling FY 2015-2017, Data analysis 10/2016 - 12/2017, and CMER approval Winter 2018. Harvesting is still on schedule
EWA Type N Characterization - Forest Hydrology | SAGE | Amy | AK | DM | GS | [23 empty] | Apr-10 | [19 empty] | 2014-08-01 | [7 empty] | Full draft report for review and approval in SAGE. Anticipated date for SAGE approval to forward to CMER July 2014
EWA Type N Riparian Effectiveness - Perennial | TWIG |  | AK | GS | GS | [7 empty] | CWA 2010 | [5 empty] | 2013-11-01 | CWA 2012 | 2015-01-01 | [10 empty] | CWA 2013 | [23 empty] | CWA 2019 | Best Available Science review and recommended alternatives approved by Policy November 2013. Working on study design for perennial reaches.
EWA Type N Riparian Effectiveness - Dry Intermittent | TWIG |  | AK | RW | GS | [7 empty] | CWA 2010 | [5 empty] | 2013-11-01 | CWA 2012 | 2015-01-02 | [10 empty] | CWA 2013 | [23 empty] | CWA 2019 | BAS review and recommended alternatives approved by Policy Nov. 2013. Policy agreed to separate the dry intermittent reaches from the perennial. Will be in the field to evaluate temporal distribution of flows in dry intermittent reaches summer 2014. TWIG will meet in fall to discuss approach for linking the perennial and dry Intermittent.
WWA Type N Buffer Integrity - Shade Effectiveness (Amphibians) | RSAG | Teresa | AK | JT |  |  | N/A | N/A | N/A | N/A | N/A | N/A | [22 empty] | N/A | N/A | [15 empty] | 2013-12-01 |  | 2014-10-01 |  | CWA 2012 | ISPR response matrix and revised report submitted for CMER approval Nov. 2013 (nonconsensus). Discussions under way about approaching an ISPR reviewer for clarification of review comments. WDFW will begin work in Sept. to get post-ISPR draft completed.
WWA Amphibians in Intermittent Streams | SAGE |  |  |  |  | 2019 Start per MPS | [6 empty] | CWA 2015 | [6 empty] | CWA 2017 | [36 empty] | Settlement Agreement scheduled start date FY 2016 with an anticipated end date of 2025 (final report). Start date of 2019 per new MPS. This project is on hold until the Hard Rock Rpt. completed to determine if needed.
TYPE F RULE GROUP
Extensive Alternative (Remote Sensing Approach) | RSAG |  |  |  |  | New Project | 2014-08-01 | [49 empty] | This pilot project replaces the prior list of Extensive Monitoring Studies and Policy has directed the RSAG to develop options for Policy’s consideration and report back to Policy at the Sept. 2014 mtg.
EWA Riparian Assessment Project (EWRAP) | SAGE | Amy | HH |  | AR |  | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | Nov- 14 | [9 empty] | Drafts of chapters 1-4 of rpt. complete and reviewed by SAGE. SAGE requested PI undertake a limited sensitivity anaylsis along with addressing report comments. PI currently organizing chapters into a single rpt. and adding a summary section. First draft of a revised rpt. will likely be available in Oct. 2014.
WWA Type F Riparian Prescription Monitoring | TWIG |  | HH |  | DS | Lean Pilot | June- 14 | [5 empty] | CWA 2014 | Jan- 14 | 2014-10-01 | [41 empty] | BAS literature review and summary rpt. to be completed by the end of Sept. TWIG to utilize BAS review in development and selection of study design alternatives, identification of a recommedned preferred alternative and report to Policy.
EWA Bull Trout Overlay Temperature (Riparian Shade/Temperature) | RSAG | Amy | AK | EC | GS |  | N/A | N/A | N/A | N/A | N/A | N/A | [43 empty] | CWA 2011 | COMPLETED - Forward to Policy May 2014. Placed on hold until Fall 2014.
EWA Type F Riparian Effectiveness Monitoring (BTO Add-on) | SAGE | Teresa | HH | DS | DS |  | N/A | N/A | N/A | N/A | N/A | N/A | [26 empty] | May-06 | May- 14 | Oct- 14 | Dec- 14 | [14 empty] | Field work for 5-year Post Harvest Survey complete. NWIFC CMER staff working on QA/QC of data.
Riparian Hardwood Conversion | RSAG | Ash | HH | AR | AR |  | N/A | N/A | N/A | N/A | N/A | N/A | [33 empty] | Jul- 13 | Jun- 14 | Jun- 14 | [7 empty] | CWA 2009 | Draft rpt. approved by RSAG and forwarded to CMER in June 2014. CMER review complete. PI working on revising rpt. based on CMER comments. 10-yr. re-sample approved by Policy and planned to occur in 2016. RSAG discussing holding off on competion of final draft of the rpt. until 10-year re-sample completed.
Extensive Riparian Status and Trends Monitoring - Temperature - Type F Westside, Type N Westside | RSAG | Teresa | HH | BE |  |  | N/A | N/A | N/A | N/A | N/A | N/A | [24 empty] | CWA 2015 | [11 empty] | Jul - 14 | [5 empty] | 2014-12-01 |  | CMER review of draft rpt. has been completed. Final revisions based on CMER comments expected by the end of 2014.
UNSTABLE SLOPE RULE GROUP
Unstable Slopes Criteria Evaluation and Development | TWIG |  | HH | GS |  | Lean Pilot | Jun- 14 | Jun- 14 |  |  |  |  | CWA 2012 | Sep- 14 | [5 empty] | CWA 2013 | [11 empty] | CWA 2014 | [24 empty] | IWT completed and forwarded to CMER their proposed qualifications for TWIG members and list of potential TWIG members. This project will require a significant amount of scoping, including a clear statement of the problem to be addressed, followed by the purpose and objectives of any project being scoped. The project may require initial data mining of the mass wasting rpt. data prior to completion of the problem statement and selection of particular projects. This may take a small group of experts with backgrounds in geology/geomorphology/hydrology to develop and recommend specific projects.
Glacial deep-seated landslide program strategy review/scoping | [6 empty] | 1905-07-07 | [49 empty] | New project - FY15
ROADS RULE GROUP
Roads Subbasin Effectiveness (Resample) | [38 empty] | 2021 | [16 empty] | CWA 2018 | Waiting to initiate re-sample
Road Prescription-Scale Effectiveness (BMP) Monitoring (TWIG) | TWIG |  | AK |  |  | Lean Pilot | [6 empty] | CWA 2013 |  | 2014-11-01 | [40 empty] | CWA 2018 | The TWIG members were approved at CMER Oct. 2013. Schedule meeting date to start work Jun 2014. The TWIG presented initial memorandum (Problem Statement, Critical Questions, Objectives) for Policy for consideration in August 2014. Requesting approval at Policy September 2014.
WETLANDS RULE GROUP
Wetlands Systematic Literature Synthesis | WETSAG | Teresa | AK | PA | AR | [15 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  | N/A | N/A |  |  |  |  | 2014-03-01 | 2014-10-01 | 2014-05-01 | 2014-11-01 |  |  | CWA 2012 | Author is Responding to ISPR comments.
Wetland/Stream Water Temperature Interactions | WETSAG | Teresa | AK |  |  | Project On Hold | [6 empty] | CWA 2012 | [43 empty] | On hold until the Wetland Strategy is completed.
Forested Wetlands Effectiveness Study | TWIG | Teresa | AK |  |  | (Lean Pilot) Project on Hold | [6 empty] | CWA 2013 | [6 empty] | CWA 2014 | [36 empty] | On hold until the Wetland Strategy is completed.
Wetlands Management Zone Effectiveness Monitoring | WETSAG | Teresa | AK |  |  | Project On Hold | [6 empty] | CWA 2011 | [43 empty] | On hold until the Wetland Strategy is completed.
Wetland Hydrologic Connectivity | [5 empty] | Project On Hold | [50 empty] | On hold until the Wetland Strategy is completed.
Wetlands Program Research/Monitoring Strategy | WETSAG | Teresa | AK | PA | AR | CWA 2013 | [8 empty] | 2014-06-30 | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2014-08-01 | 2014-11-01 |  |  |  | WetSAG has completed multiple meetings working on the strategy with the goal to complete work in June/July 2014 for CMER review. To Policy for review around November 2014.
WILDLIFE RULE GROUP
RMZ-Resample (Birds) | LWAG |  | AK | SP | [44 empty] | 2014-01-01 |  | 2014-07-01 |  | 2014-08-01 | 2014-08-01 |  |  | Submitted to CMER for final CMER approval. To Policy for consideration Nov/Dec. 2014.
INTENSIVE WATERSHED-SCALE MONITORING TO ASSESS CUMULATIVE EFFECTS
Watershed Scale Assessment of Cumulative Effects | [12 empty] | CWA 2015 | [6 empty] | CWA 2017 | [11 empty] | CWA 2018
Table Legend (Colors): |  | CWA Priorities
Committee Assigned |  | (*R) = revised April 2010 |  |  |  | Note: This color is provided to emphasis the column that communicates which science committee is currently responsible for overseeing the completion of the project.
Project Milestone | [5 empty] | Note: The milestones are located in the spreadsheet before the respective tasks for that milestone. The estimated timeframe of the milestones is the total months to complete the tasks for the respective milestone. Or, the total of all of the months it takes to complete the subtasks that follow the milestone.
Task completed | [5 empty] | Note: The spreadsheet represents the projects in the program in a linear fashion. The reality is that some of the tasks occur simultaneously. The timeframe provided in months is for reference purposes and as a gauge to determine how long it could be if the project moves through its lifecycle in an a typical fashion.
Project Milestone/Task not applicable to the project | N/A |  |  |  |  | Note: The N/A represents the tasks within the lifecycles of the project that were not applicable to that project. The reason for the task not being completed is different for each project and therefor not provided in the table.
Current Lifecycle Phase of the Project | [5 empty] | Note: This color respresents the current phase of the project.
Clean Water Act Milestone | [5 empty] | Note: This color represents a CWA milestone and in most cases there is a note provided on that milestone or tasks that provides the current status as provided in the lastest quarterly update by DOE (7/22/13).
Anticipated Start Date | 2011 |  |  |  |  | Note: The year in the cells with no color represents the fiscal year that milestone or task is intended to start work. This is based on the FY 2014-2022 Adaptive Management Program Budget (May 2013-Board Approved).
Human Resources | [5 empty] | AK- Amy Kurtenbach, HH- Howard Hammerle, GS- Greg Stewart, AS- Ash Roorbach, DS- Dave Schuett-Hames, BE- Bill Ehinger, AM-Aimee McIntyre, PA-Paul Adamus, JT-Julie Tyson, DM-Dan Miller, RW-Rick Woodsmith
Note on H3: jamm490: Problem statement, Purpose, Critical questions, etc
Note on J3: akur490: Iterative document completed with Scoping and revised throughout lifecycle of the project.
Note on L3: akur490: Iterative document that is revised throughout the lifecycle of the project.
Note on S3: akur490: ISPR not needed in this phase.
Note on BE8: Windows User: CWA: On track
Note on BE9: Windows User: CWA: On track
Note on AG12: Windows User: CWA: Data Collection began in the summer of 2012
Note on BE12: Windows User: Underway
Note on N14: Windows User: Completed. June 2013 Policy approved purpose, obj, and CQ
Note on U14: Windows User: CWA: Underway. In June 2013 the IWT began the process of developing study design options. The Type N Hydro. Study data (Avail. Summer/Fall 2013) will be used to estab. Test strata for the study.
Note on AG14: Windows User: CWA: Underway. In study design development phase.
Note on BE14: Windows User: CWA: Underway. Project will likely be completed later than this milestong due to the delay in project initiation.
Note on N15: Windows User: Completed. June 2013 Policy approved purpose, obj, and CQ
Note on U15: Windows User: CWA: Underway. In June 2013 the IWT began the process of developing study design options. The Type N Hydro. Study data (Avail. Summer/Fall 2013) will be used to estab. Test strata for the study.
Note on AG15: Windows User: CWA: Underway. In study design development phase.
Note on BE15: Windows User: CWA: Underway. Project will likely be completed later than this milestong due to the delay in project initiation.
Note on BE16: Windows User:
Note on N17: Windows User: CWA: Not progressing. Porject milestones exists only if needed to fill research gaps left from Type N. Hard Rock report
Note on U17: Windows User: CWA; Not progressing
Note on N21: Windows User: CWA: Not Progressing. IWT approved by CMER but work has not begun.
Note on AL25: Windows User: CWA: Underway
Note on N27: Windows User: CWA: Not progressing. An IWT was approved by CMER, and a draft charter assembled but work has not begun. On FY 2014 budget.
Note on U27: Windows User: CWA: Not Progressing. No work has occurred. On FY 2014 budget
Note on AG27: Windows User: CWA: Not Progressing. IWT approved by CMER. Charter assembled, not work has begun. On FY 2014 budget
Note on N28: Windows User: CWA: Off Track, No work has occurred. On FY 2015 budget.
Note on U28: Windows User: CWA: No work has occurred On FY 2015 budget
Note on BE30: Windows User: CWA: Not Progressing
Note on N31: Windows User: CWA: Not Progressing. On FY 2014 Budget
Note on BE33: Windows User: CWA: Final report expected in late 2013 to mid 2014
Note on N35: Windows User: CWA: Not progressing. Scoping will not be initiated until the Lit. Synthesis is completed.
Note on U35: Windows User: CWA: Not progressing. Scoping will not be initiated until the Strategy completed late 2013
Note on G38: Windows User: CWA: Underway.
Note on N43: Windows User: CWA: Not progressing
Note on U43: Windows User: CWA: Not Progressing
Note on AG43: Windows User: CWA: Not progressing
Note on BE44: Windows User: CWA: Not Progressing

## Flagging Triggers
Flagging
As a general rule, the Project Managers will notify AMPA and CMER as soon as issues are identified that could affect a project's progress.
Major Milestone |  |  | Project Tasks Not Completed by… |  | Flag x months after initiating Major Milestone | Who Notified
CMER Project Planning Initiated (7 months through CMER & Policy)
| SRSAG | Amy | Dave/Greg | 2010-09-01 | 2 | Policy | 2010-09-01 | 2010-09-01 | 2011-02-01 | ?? | 2011-03-01 | 2010-11-01
|  | SAG Supported Project Plan |  |  | 4 | CMER
|  | CMER Supported Project Plan |  |  | 7 | CMER
CMER Approved Scoping Paper (7 months through CMER & Policy)
|  | CQ, Objectives, Data Needs, Options, & BAS Identified |  |  | 4 | CMER/Policy
| * | SAG Approved Scoping Paper for CMER Review |  |  | 6 | CMER
|  | CMER Approval of Scoping Paper |  |  | 7 | Policy
CMER Approved Final Study Design (18 months through CMER & to Policy) | [12 empty] | 2010-10-01 | 2011-02-01 | 2011-07-01 | 2011-11-01 |  | 2012-02-01 | 2012-10-01 |  | 2012-12-01
| * | SAG Approved Study Design |  |  | 6 | CMER | [10 empty] | 2010-10-01 | 2010-10-01 | 2011-07-01 |  | 2011-09-01
|  | CMER Approved Study Design |  |  | 8 | CMER
|  | ISPR Review of Study Plan Complete |  |  | 16 | CMER/Policy
|  | CMER Approved Final Study Plan |  |  | 18 | CMER/Policy
[14 empty] | 2010-05-01 | 2011-10-01 | 2011-02-01
*Before starting the study design, the Problem statement, Questions, Objectives, and study approach should have already been approved by CMER. Policy should have approved the Problem statement and Questions - and possibly the Objectives. The Study approach in general should be left to CMER, unless there are significant benefit/cost issues associated with alternative approaches.
Final Study Plan to Policy (1 month to forward to Policy)
|  | Final Study Plan Forwarded to Policy for Consideration |  |  | 1 | Policy | [11 empty] | 2010-12-01 | 2011-08-01
Contract Completed (4 months for RFQ and award of contract) | [19 empty] | 2010-09-01 | 2010-11-01 | 2011-02-01
|  | Draft RFQ, RFP and Award Contract |  |  | 4 | CMER
Field/Research Completed (15 months for non-field work tasks, total time frame is project specific)
|  | Field manual completed |  |  | 3 | CMER
|  | QA/QC Methods and Plan Completed |  |  | 6 | CMER
|  | Site Selection Completed (as applicable) |  |  | 11 | CMER
|  | Data Collected/Field Work Completed |  |  | PS | CMER/Policy
Type F Experimental Buffer Treatment |  | SAG Approval of Database |  |  | PS+4 | CMER
5
CMER Approved Final Project Report Completed (25 months through CMER and to Policy, including 6 questions)
|  | Methods/Data/Statistical Analysis SAG Supported |  |  | 5 | CMER
|  | SAG Approved Project Report (for CMER review) |  |  | 9 | CMER
|  | CMER Approved Project Report (for ISPR Review) |  |  | 12 | CMER/Policy
|  | ISPR Review of Project Report (with CMER approved matrix) |  |  | 20 | CMER/Policy
|  | CMER Approved Final Report |  |  | 22 | CMER/Policy
|  | SAG/CMER Findings Report |  |  | 25 | CMER/Policy
Month count starts over at the beginning of each milestone.
Note on C8: jamm490: Minimum: rule group, type of r/m (rule tool, effect m, exten m, inten m, problem statement, purpose, critical questions

## CMER Tasks
| Scoping Phase | [5 empty] | Study Design Phase | [5 empty] | Contracting |  | Field Work Phase
Project Initiation Date and Scoping | Project Charter with rule group, type of research/monitoring, critical questions, problem and purpose statements, etc identified | Project Plan approved by SAG | Project questions, objectives, and data requirements | Options and BAS developed | Scoping document approved by SAG | Scoping document approved by CMER | First draft of study design | Study design approved by SAG | Study design approved by CMER for ISPR review | ISPR completed | Final study design approved by CMER | Final study design accepted by Policy | Draft RFQ, RFP, and contract, if needed | Contract awarded, if needed | Field Manual Completed | Final QA/QC methods completed | Initial sites selected | Final sites selected | Critical date to initiate field work | Quarterly updates throughout field work | Sites Harvested on time iand per study design | Field work complete | Database approved by SAG | Data analysis, including statistical analysis | Final report approved by SAG | Final report approved by CMER, ready for ISPR | ISPR Complete | Final report approved by CMER | SAG/CMER approval of Findings Report
Expected months per task | 2 | 3 | 2 | 2 | 2 | 1 | 4 | 2 | 2 | 8 | 2 | 1 | 3 | 1 | 3 | 3 | 2 | 3 | Assume BACI with 4 data collection seasons, 1 treatment season |  |  | 0 | 4 | 5 | 4 | 3 | 8 | 2 | 3
Linear cumulative time (months) | 2 | 5 | 7 | 9 | 11 | 12 | 16 | 18 | 20 | 28 | 30 | 31 | 34 | 35 | 38 | 41 | 43 | 46 |  |  |  | 46 | 50 | 55 | 59 | 62 | 70 | 72 | 75
[13 empty] | If contract needed | If contract needed | Work begins with SAG approved study design |  |  |  | Use to back calculate when project initation must occur |  | Set for specific project | Adjust to reflect end of project specific field season
Note on O5: Teresa Moon: Total timeframe to complete tasks within milestone

## CMER Coordinated Review
Coordinated CMER Review Timeframe
Project Name | SAG | Anticipated CMER schedule | Phase of CMER Approval* | Project Manager | CMER Reviewer #1 | CMER Reviewer #2 | CMER Reviewer #3 | CMER Reviewer #4 | CMER Reviewer #5
Road Sub Basin | UPSAG | 2010-06-01 | ISPR Review | Amy Kurtenbach | Doug Martin | Nancy Sturhan | Dick Miller | Mark Hayes | Chris Mendoza
Desktop Analysis | RSAG | Complete | Final CMER | Amy Kurtenbach | Chris Mendoza | Dick Miller | Joe Murray | Assigned | Assigned
Type N Experimental Amphibian Genetics | LWAG | 2010-08-01 | ISPR Matrix | Teresa Miskovic | Terry Jackson | Chris Mendoza | Adrian Spidle
Extensive Westside Type F | RSAG | 2010-11-01 | CMER Review | Teresa Miskovic | Nancy Sturnhan | Leslie Lingley | Mark Mobbs | Dick Miller
Extensive Eastside Type F | RSAG | 2010-07-01 | CMER review of CMER revisions | Teresa Miskovic | Todd Balwin | Leslie Lingley | Mark Hayes | Chris Mendoza (N.O.)
Extensive Westside Type N | RSAG | 2010-11-01 | CMER Review | Teresa Miskovic | Nancy Sturhan | Mark Hayes
Post Mortem | UPSAG | 2010-09-01 | CMER comment Matrix | Amy Kurtenbach | Terry Jackson | Paul Kennard (Enviro. Caucus) | Nancy Sturhan | Mark Hicks | Doug Martin | AJ Kroll | Alice Shelly (CMER Contract) | Dick Miller
Type N Westside BCIF | RSAG | 2010-09-01 | CMER Review | Teresa Miskovic | Chris Mendoza | Nancy Sturhan | AJ Kroll
Bulltrout Solar | RSAG | June/July | CMER comment Matrix | Amy Kurtenbach | Todd Baldwin | Leslie Lingley | Steve McConnell
Wetland Mitigation Effectiveness Study Design | WETSAG | 2010-07-01 | CMER review of CMER revisions | Teresa Miskovic | Chris Mendoza | Nancy Sturhan | Leslie Lingley | Mark Hicks (N.O.) | Dick Miller (N.O)
Updated June 14, 2010
COMPLETED CMER PROCESS (red font~italic)